## Dashboard
ERP Implementation · Budget & Timeline Dashboard
Phases: Initiate → Design → Build → Test → Deploy · All figures pull live from Budget Tracker, Milestones & Resources
| Total Budget | Total Committed | Total Actual | Remaining | % Spent | # Milestones Complete | # Overdue | Est. Resource Cost
| 472000 | 0 | 0 | 472000 | 0% | 0 | 23 | 0
Phase Budget Summary
| Phase | Planned ($) | Committed ($) | Actual ($) | Remaining ($) | % Spent | Variance ($) | Status
| Initiate | 31000 | 0 | 0 | 31000 | 0% | -31000 | ■ Over Budget
| Design | 100000 | 0 | 0 | 100000 | 0% | -100000 | ■ Over Budget
| Build | 151000 | 0 | 0 | 151000 | 0% | -151000 | ■ Over Budget
| Test | 77000 | 0 | 0 | 77000 | 0% | -77000 | ■ Over Budget
| Deploy | 68000 | 0 | 0 | 68000 | 0% | -68000 | ■ Over Budget
| ALL PHASES | 472000 | 0 | 0 | 472000 | 0% | -472000
Milestone Progress by Phase
| Phase | Total Milestones | Complete | Overdue | Pending | % Complete | Next Milestone
| Initiate | 4 | 0 | 4 | 0 | 0% | Project Closure
| Design | 5 | 0 | 5 | 0 | 0% | Project Closure
| Build | 5 | 0 | 5 | 0 | 0% | Project Closure
| Test | 5 | 0 | 5 | 0 | 0% | Project Closure
| Deploy | 5 | 0 | 4 | 1 | 0% | Project Closure
● On Track = variance <5% ▲ Watch = 5–15% ■ Over Budget = >15% ✓ Complete ⚠ Overdue ○ Pending

## Budget Tracker
ERP Implementation Budget Tracker
Blue = input · All totals and variances calculate automatically · Update actuals as you spend
Cost Category | Phase | Planned ($) | Committed ($) | Actual ($) | Remaining ($) | % Spent | Variance ($) | Status
INITIATE
Project Charter & Governance | Initiate | 8000 | 0 | 0 | 8000 | 0% | -8000 | ■ Over Budget
Business Case Development | Initiate | 6000 | 0 | 0 | 6000 | 0% | -6000 | ■ Over Budget
Vendor RFP & Evaluation | Initiate | 12000 | 0 | 0 | 12000 | 0% | -12000 | ■ Over Budget
Project Kickoff & Setup | Initiate | 5000 | 0 | 0 | 5000 | 0% | -5000 | ■ Over Budget
DESIGN
Business Process Mapping | Design | 22000 | 0 | 0 | 22000 | 0% | -22000 | ■ Over Budget
System Configuration Design | Design | 35000 | 0 | 0 | 35000 | 0% | -35000 | ■ Over Budget
Data Migration Design | Design | 15000 | 0 | 0 | 15000 | 0% | -15000 | ■ Over Budget
Integration Architecture | Design | 18000 | 0 | 0 | 18000 | 0% | -18000 | ■ Over Budget
Design Workshops | Design | 10000 | 0 | 0 | 10000 | 0% | -10000 | ■ Over Budget
BUILD
Core System Configuration | Build | 55000 | 0 | 0 | 55000 | 0% | -55000 | ■ Over Budget
Custom Development | Build | 40000 | 0 | 0 | 40000 | 0% | -40000 | ■ Over Budget
Data Migration Build | Build | 20000 | 0 | 0 | 20000 | 0% | -20000 | ■ Over Budget
Integration Development | Build | 28000 | 0 | 0 | 28000 | 0% | -28000 | ■ Over Budget
Technical Documentation | Build | 8000 | 0 | 0 | 8000 | 0% | -8000 | ■ Over Budget
TEST
Unit & Integration Testing | Test | 18000 | 0 | 0 | 18000 | 0% | -18000 | ■ Over Budget
User Acceptance Testing (UAT) | Test | 22000 | 0 | 0 | 22000 | 0% | -22000 | ■ Over Budget
Performance Testing | Test | 10000 | 0 | 0 | 10000 | 0% | -10000 | ■ Over Budget
Defect Resolution | Test | 15000 | 0 | 0 | 15000 | 0% | -15000 | ■ Over Budget
Training Material Development | Test | 12000 | 0 | 0 | 12000 | 0% | -12000 | ■ Over Budget
DEPLOY
End-User Training | Deploy | 16000 | 0 | 0 | 16000 | 0% | -16000 | ■ Over Budget
Data Cutover & Migration | Deploy | 14000 | 0 | 0 | 14000 | 0% | -14000 | ■ Over Budget
Go-Live Support (Hypercare) | Deploy | 20000 | 0 | 0 | 20000 | 0% | -20000 | ■ Over Budget
Post Go-Live Stabilization | Deploy | 12000 | 0 | 0 | 12000 | 0% | -12000 | ■ Over Budget
Project Closure & Handover | Deploy | 6000 | 0 | 0 | 6000 | 0% | -6000 | ■ Over Budget
ALL
Contingency Reserve | All | 30000 | 0 | 0 | 30000 | 0% | -30000 | ■ Over Budget
Change Order Buffer | All | 15000 | 0 | 0 | 15000 | 0% | -15000 | ■ Over Budget
Initiate Subtotal |  | 31000 | 0 | 0 | 31000 | 0% | -31000
Design Subtotal |  | 100000 | 0 | 0 | 100000 | 0% | -100000
Build Subtotal |  | 151000 | 0 | 0 | 151000 | 0% | -151000
Test Subtotal |  | 77000 | 0 | 0 | 77000 | 0% | -77000
Deploy Subtotal |  | 68000 | 0 | 0 | 68000 | 0% | -68000
All Subtotal |  | 45000 | 0 | 0 | 45000 | 0% | -45000
TOTAL PROJECT BUDGET |  | 472000 | 0 | 0 | 472000 | 0% | -472000

## Milestones
Milestone Tracker
Enter planned dates and owner. Update actual date and complete checkbox when milestone is achieved.
| Milestone | Phase | Planned Date | Actual Date | Owner | Days Variance | % Phase Done | Status
| Project Start Date: | 2025-01-06
INITIATE
1 | Project Charter Signed | Initiate | 2025-01-20 |  |  |  |  | ⚠ Overdue
2 | Steering Committee Established | Initiate | 2025-01-27 |  |  |  |  | ⚠ Overdue
3 | Vendor Contract Executed | Initiate | 2025-02-20 |  |  |  |  | ⚠ Overdue
4 | Project Kickoff Complete | Initiate | 2025-02-25 |  |  |  |  | ⚠ Overdue
DESIGN
5 | Current-State Process Maps Done | Design | 2025-03-27 |  |  |  |  | ⚠ Overdue
6 | Future-State Design Approved | Design | 2025-04-26 |  |  |  |  | ⚠ Overdue
7 | Data Migration Strategy Signed Off | Design | 2025-05-06 |  |  |  |  | ⚠ Overdue
8 | Integration Architecture Approved | Design | 2025-05-16 |  |  |  |  | ⚠ Overdue
9 | Design Phase Sign-Off | Design | 2025-05-26 |  |  |  |  | ⚠ Overdue
BUILD
10 | Core Configuration Complete | Build | 2025-07-25 |  |  |  |  | ⚠ Overdue
11 | Custom Dev Complete | Build | 2025-08-24 |  |  |  |  | ⚠ Overdue
12 | Integrations Built & Unit Tested | Build | 2025-09-08 |  |  |  |  | ⚠ Overdue
13 | Data Migration Scripts Validated | Build | 2025-09-18 |  |  |  |  | ⚠ Overdue
14 | Build Phase Sign-Off | Build | 2025-10-03 |  |  |  |  | ⚠ Overdue
TEST
15 | SIT Complete | Test | 2025-11-02 |  |  |  |  | ⚠ Overdue
16 | UAT Kick-Off | Test | 2025-11-12 |  |  |  |  | ⚠ Overdue
17 | UAT Sign-Off | Test | 2025-12-12 |  |  |  |  | ⚠ Overdue
18 | Performance Testing Complete | Test | 2025-12-22 |  |  |  |  | ⚠ Overdue
19 | Go/No-Go Decision | Test | 2026-01-06 |  |  |  |  | ⚠ Overdue
DEPLOY
20 | Training Complete | Deploy | 2026-01-21 |  |  |  |  | ⚠ Overdue
21 | Data Cutover Complete | Deploy | 2026-02-05 |  |  |  |  | ⚠ Overdue
22 | Go-Live | Deploy | 2026-02-10 |  |  |  |  | ⚠ Overdue
23 | Hypercare Period End | Deploy | 2026-03-12 |  |  |  |  | ⚠ Overdue
24 | Project Closure | Deploy | 2026-04-01 |  |  |  |  | ○ Pending
Formulas:
Status = IF([Actual Date]<>"","✓ Complete",IF(TODAY()>[Planned Date],"⚠ Overdue","○ Pending"))

## Resources
Resource Utilization Tracker
Blue = input. Planned hours and daily rates drive cost. Actual hours update as work progresses.
Role / Resource | Daily Rate ($) | Initiate Planned Days | Initiate Actual Days | Design Planned Days | Design Actual Days | Build Planned Days | Build Actual Days | Test Planned Days | Test Actual Days | Deploy Planned Days | Deploy Actual Days | Total Planned Cost | Total Actual Cost
Project Manager | 950 | 15 | 0 | 20 | 0 | 30 | 0 | 20 | 0 | 15 | 0 | 95000 | 0
Functional Consultant | 850 | 5 | 0 | 30 | 0 | 40 | 0 | 25 | 0 | 10 | 0 | 93500 | 0
Technical Consultant | 900 | 3 | 0 | 15 | 0 | 35 | 0 | 20 | 0 | 5 | 0 | 70200 | 0
Data Migration Lead | 825 | 2 | 0 | 12 | 0 | 18 | 0 | 15 | 0 | 5 | 0 | 42900 | 0
Integration Developer | 875 | 0 | 0 | 10 | 0 | 28 | 0 | 15 | 0 | 3 | 0 | 49000 | 0
Internal SME — Finance | 350 | 5 | 0 | 20 | 0 | 15 | 0 | 20 | 0 | 8 | 0 | 23800 | 0
Internal SME — Ops | 350 | 3 | 0 | 15 | 0 | 12 | 0 | 18 | 0 | 6 | 0 | 18900 | 0
Internal SME — IT | 400 | 5 | 0 | 10 | 0 | 20 | 0 | 15 | 0 | 8 | 0 | 23200 | 0
Change Manager | 750 | 5 | 0 | 10 | 0 | 8 | 0 | 12 | 0 | 15 | 0 | 37500 | 0
Training Lead | 700 | 0 | 0 | 5 | 0 | 5 | 0 | 15 | 0 | 12 | 0 | 25900 | 0
TOTAL |  | 43 | 0 | 147 | 0 | 211 | 0 | 175 | 0 | 87 | 0 | 479900 | 0

## Variance Log
Variance Log & Change Register
Log every budget change and variance event. Links to Budget Tracker for automatic status flagging.
# | Cost Category | Phase | Original Budget ($) | Current Budget ($) | Actual to Date ($) | Variance ($) | Variance (%) | Root Cause / Notes | Action Required
1 | Project Manager | Initiate | 14250 | 14250 | 0 | -14250 | -100%
2 | Business Case Development | Initiate | 6000 | 6000 | 0 | -6000 | -100%
3 | System Configuration Design | Design | 35000 | 35000 | 0 | -35000 | -100%
4 | Core System Configuration | Build | 55000 | 55000 | 0 | -55000 | -100%
5 | UAT | Test | 22000 | 22000 | 0 | -22000 | -100%
6 | Go-Live Support | Deploy | 20000 | 20000 | 0 | -20000 | -100%
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
21 | [5 empty] | 0
22 | [5 empty] | 0
23 | [5 empty] | 0
24 | [5 empty] | 0
25 | [5 empty] | 0
26 | [5 empty] | 0